## Scope
Assignment-38
Feature List
ID | Features | Description | Priority | Dev Estimate Hours | Dev Complete (%)
1 | Submitted Task to developers | E-mail to team to say "Thank you for choosing E-Giants--Task 1 Allotted" | MUST | 2 | 100%
2 | Module 1 Developing | Allotted task to developer | MUST | 4 | 100%
3 | Bulk e-mail notifications | Notifications to developers to know whether module 1 is finished or not | SHOULD | 1 | 100%
4 | Report - Status detail | Detail report of Assignment-38 | MUST | 1 | 100%
| Submission warning | If submission not successful then we receive warning | SHOULD | 1 | 100%

## Progress
Date with time | Original Scope(%) | Contingency(%) | Story Points Complete(%) | Dev Complete(%)
2017-05-22 | 100% | 110% | 50% | 20%
2017-05-22 | 100% | 110% | 50% | 24%
2017-05-22 | 100% | 110% | 75% | 30%
2017-05-22 | 100% | 110% | 80% | 46%
2017-05-23 | 100% | 110% | 82% | 52%
2017-05-23 | 100% | 110% | 85% | 65%
2017-05-23 | 100% | 110% | 94% | 80%
2017-05-23 | 100% | 110% | 96% | 97%
2017-05-23 | 100% | 110% | 100% | 100%
Note: It’s a progress of the project by E-Giants Technologies LLC