## Cover Sheet
Assignment-38 Functional Specification document
Author: | Nikhil K Konda
Version: | This is a living document and is not formally version controlled.
overview: | This document is the Functional specification for Assignment-38
This document specifies what the system will do & how it will do.
Structure: | Functional Specification consistes of a set of "Stories"
Each story describes some aspect of the system's behaviour, either functional or non-functional.
A story is the smallest unit of system delivery - a story is either delivered or it is not.
The "Summary" worksheet is an inventory of all the stories, along with various information for each one.
The "Details" worksheet contains the detailed specification for each story.
Each story is specified in "use case" format
The "Users" workheet specifies all Users.
The "Stats" worksheets show development progress for individual increments, in the form of a "burn down chart"

## Users
User Name | Description
General User | Any user, whether logged in or not
Anonymous User | Any user who is not logged in
Logged In User | Any user who is logged in
Organisation User | User responsible for basic operations within their organisation
Sys Admin | System administrator

## Stats(Summary)
Story Points Count Summary
Increment | Story Points | Developer Working Hours | Velocity
Module(Task1) | 12 | 10 | 1.2
Total | 12 | 10 | 1.2
|  | Actually its not Working Hours sir its Days as assignment is deadline for tomorrow.I have calculated in hours sir |  | Velocity = Storypoints/Man working hours

## Stats(H3)
Total Story points | Total Developrs Working Hours | Estimated velocity | Total Story points Delivered | Actual Velocity |  | Date | Developer Working Hours | Developer working Hrs (Cummulative) | Story points(Est Cumulative) | Story points(Actual Today) | Story points(Actual Cumulative) | NIKHIL | TAGORE | VIGNAN | DHARMA | SHIVA
12 | 10 | 1.2 | 12 | 1.2
[5 empty] | Week 1(Only 2 days) | 2017-05-14 | 3 | 3 | 3.6 | 5 | 5 | 1 | 0 | 1 | 1 | 0
[6 empty] | 2017-05-14 | 0
[6 empty] | 2017-05-15 | 5 | 5 | 3.6 | 7 | 7 | 1 | 1 | 1 | 0 | 1
[6 empty] | 2017-05-15 | 0
[6 empty] | 2017-05-15 | 0
Week 2
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.